## Sprint 1
Week #1 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7*4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06
40
28
Understanding Project Requirements | Analyse the given project requirements with team and list out grey areas if any | All | 20 | 0 | 0 | 4 | 8 | 4 | 4 | 0
Decide Technology Stack | Discuss with team on which technology stack is best to use for given project | All | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0
Discuss Components | Discuss various components, what to proceed with and how | All | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0
|  | Total | 28 | 28 | 28 | 20 | 12 | 8 | 0 | 0 | Ideal Burndown
|  | Ideal | 28 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | Remaining Hrs (Total)
Team:
Shrey | 7 hours / Week
Rushikesh | 7 hours / Week
Shreemathi | 7 hours / Week
Madhurima | 7 hours / Week
Total Available Hours During Sprint: | 28

## Sheet4 (hidden)
day | ideal | total
2022-02-28 | 28 | 28
2022-03-01 | 24 | 28
2022-03-02 | 20 | 20
2022-03-03 | 16 | 12
2022-03-04 | 12 | 8
2022-03-05 | 8 | 0
2022-03-06 | 4 | 0
|  | 28 | 24 | 20 | 16 | 12 | 8 | 4